## Tasks
Priority | Rank | Status | Section | Sub Section | Sub-Area | Task | SubTask | Estimated Hours | Completed | Totals | Date Added | Notes
A | 2 |  | Infrastructure |  |  | Changed directory structure to CommandLineTools |  |  |  |  | 2020-06-04
A | 5 |  | Infrastructure |  |  | Fix all code analysis (sniff) errors. |  |  |  |  | 2020-06-12
A | 10 |  | Infrastructure |  |  | Review all PHP files and replace hard coded text strings |  |  |  |  | 2020-06-08
A | 11 |  | Infrastructure |  |  | Review all PHP files and update all __, _e, _n and their derived function (ex 'esc_html_e). Use printf when variables are involved. Use _x and _ex as needed |  |  |  |  | 2020-06-08
A | 12 |  | Infrastructure |  |  | Add require dependency, such as mininum a PHP version |  |  |  |  | 2020-06-04
A | 14 |  | Infrastructure |  |  | Missing phpdoc |  |  |  |  | 2020-06-04
A | 15 |  | Infrastructure |  |  | Move css to enqueue styles |  |  |  |  | 2020-06-04
A | 20 |  | Infrastructure |  |  | Additional customization to minimize size of bootstrap files. | BootStrapCustomization/config.json |  |  |  | 2020-06-04
A | 28 |  | Infrastructure |  |  | The assets compilation should performed using grunt or gulp. Also, the Gruntfile.js or Gulp.js should included in the theme. |  |  |  |  | 2019-09-04
A | 29 |  | Infrastructure |  |  | The external assets should handled using bower.js or npm, and the external assets should included in the theme assets using relative paths, and this mean, that the external assets, should not duplicated in the theme assets folder from the node_components or the bower_components folders. |  |  |  |  | 2019-09-04
A | 31 |  | Infrastructure |  |  | Theme to be speed optimized from the start (actually what we need is to see best practices). |  |  |  |  | 2019-09-04
A | 41 |  | Infrastructure |  |  | I need you to use the Option Tree plugin in order to register the theme settings ( it's up to you what configuration you like to apply. Me, I am only interested to see how you use the plugin). |  |  |  |  | 2019-09-04
A | 42 |  | Infrastructure |  |  | Instead you should create your own micro-framework using the composer, with required external libraries (in case you use external libraries), and configure the composer to auto-load your micro-framework using the psr-4. |  |  |  |  | 2019-09-04 | Thus the functions.php should not be more than 30 - 50 lines of code.
A | 51 |  | Infrastructure |  |  | Update readme.txt |  |  |  |  | 2020-05-25
A | 108 |  | Infrastructure | Css |  | Clarify build system, integration of non-sass css files |  |  |  |  | 2020-05-25
A | 109 |  | Infrastructure | Css |  | each component in the WordPress theme, should be mapped in a single scss file. Thus, a single Widget, should have a single SCSS file, a single theme file should have a single SCSS file (ie: single.php -> single.scss, page.php -> page.scss) |  |  |  |  | 2019-09-04
A | 110 |  | Infrastructure | Css |  | Theme uses the Bootstrap CSS Framework. |  |  |  |  | 2019-07-15 | Merge in bootstrap
A | 111 |  | Infrastructure | Css |  | Edit Gruntfile.js io include the real css files |  |  |  |  | 2019-07-15
A | 112 |  | Infrastructure | Css |  | Edit header.php, index.php and functions to get proper type of css file. |  |  |  |  | 2019-07-15
A | 113 |  | Infrastructure | Css |  | The CSS should be generated using SCSS. |  |  |  |  | 2019-07-15
A | 114 |  | Infrastructure | Css |  | the SCSS should produce both style.css as well the style.min.css. |  |  |  |  | 2019-07-15
A | 121 |  | Infrastructure | Css |  | Minify |  |  |  |  | 2019-07-15
A | 130 |  | Infrastructure | Js |  | The JS should compiled in single file. |  |  |  |  | 2019-07-14
A | 131 |  | Infrastructure | Js |  | The final JS production should have the scripts.js and the scripts.min.js. |  |  |  |  | 2019-07-14
A | 132 |  | Infrastructure | Js |  | each component in the WordPress theme, should be mapped in a single js file as I do with the scss. (ie: js related to index.php -> index.js, custom-widget.php -> custom-widget.js) |  |  |  |  | 2019-09-04
A | 134 |  | Infrastructure |  |  | edit Gruntfile.js to include uglify |  |  |  |  | 2019-07-15
A | 136 |  | Infrastructure |  |  | edit build.cmd to include grunt uglify |  |  |  |  | 2019-07-15
A | 140 |  | Infrastructure |  |  | edit Gruntfile.js to include watch |  |  |  |  | 2019-07-15
A | 142 |  | Infrastructure |  |  | edit build.cmd to include grunt watch |  |  |  |  | 2019-07-15
A | 147 |  | Infrastructure | Js |  | Minify |  |  |  |  | 2019-07-15
A | 150 |  | Infrastructure |  |  | Make a test page for all templates |  |  |  |  | 2016-09-23 | Migrated
A | 151 |  | Infrastructure |  |  | For the functions.php, I don't want to see all the functions in one file. |  |  |  |  | 2019-09-04
B | 23 |  | Core Functionality |  |  | In the front end, the theme should utilise the Bootstrap Nav component for the menu, that is going to be also functional when the site is displayed in mobile devices. |  |  |  |  | 2019-07-14 | This mean, that the menu should be responsive, and when the screen size is beyond the appropriate break point, will display the hamburger menu.
B | 33 |  | Core Functionality |  |  | The theme should have a Gallery post type |  |  |  |  | 2019-09-04
B | 34 |  | Core Functionality |  |  | The theme should have a Gallery Categories Taxonomy. |  |  |  |  | 2019-09-04
B | 35 |  | Core Functionality |  |  | The Gallery post type, should have a meta box, that will allow the end user to upload as many images as he like ( using the native WordPress Media Dialog ), and they will also have the opportunity to change the images order as well they will be able to remove them one by one. |  |  |  |  | 2019-09-04
B | 36 |  | Core Functionality |  |  | The Gallery post type, should have a meta box, they will also have the opportunity to change the images order as well they will be able to remove them one by one. |  |  |  |  | 2019-09-04
B | 37 |  | Core Functionality |  |  | The Gallery post type, should have a meta box, they will be able to remove them one by one. |  |  |  |  | 2019-09-04
B | 38 |  | Core Functionality |  |  | The meta box in the Gallery post type should developed using code and not plugins. |  |  |  |  | 2019-09-04
B | 39 |  | Core Functionality |  |  | I need you to implement the gallery archive page |  |  |  |  | 2019-09-04
B | 40 |  | Core Functionality |  |  | I need you to implement the single page layout for a single gallery, that is going to display the gallery images, in the same order as the admins order the images in the WordPress dashboard. |  |  |  |  | 2019-09-04
B | 44 |  | Core Functionality |  |  | Register the microdata for all the required parts (you should decide what micro-data you want to register). |  |  |  |  | 2019-09-04
B | 46 |  | Core Functionality |  |  | Add social media support |  |  |  |  | 2019-07-19
B | 48 |  | Core Functionality |  |  | Add pageup | add toTop |  |  |  | 2016-09-23 | Migrated
B |  |  | Core Functionality |  |  | test all templates | general |  |  |  | 2016-09-23 | Migrated
B |  |  | Core Functionality |  |  | test all templates | breadcrumbs |  |  |  | 2016-09-23 | Migrated
B |  |  | Core Functionality |  |  | bootstrap header tag |  |  |  |  | 2017-01-19 | Migrated
B |  |  | Core Functionality |  |  | child | move default front page image to theme |  |  |  | 2016-09-23 | Migrated
B |  |  | Core Functionality |  |  | standarize menu |  |  |  |  | 2019-09-04 | Migrated
B |  |  | Core Functionality |  |  | Include comments_template(). |  |  |  |  | 2019-09-04 | Migrated
B |  |  | Design | bootstrap |  | base column class style based on whether right column showing |  |  |  |  | 2017-01-19 | Migrated
B |  |  | Design |  |  | Add bigger bottom margin to sections |  |  |  |  | 2016-07-05 | Migrated
B |  |  | Design |  |  | adjust child theme for paddings because of -fluid change |  |  |  |  | 2017-01-19 | Migrated
C | 4 |  | Merge |  |  | Merge in other PHP template files | from dzw, tmh, inferret, ofj, lynx, gopon |  |  |  | 2019-07-14 | From other themes
C | 7 |  | Merge |  |  | Merge in _s theme | layout |  |  |  | 2019-09-11
C | 8 |  | Merge |  |  | Merge in _s theme | template-parts |  |  |  | 2019-09-11
C | 9 |  | Merge |  |  | Merge in _s theme | languages |  |  |  | 2019-09-11
C | 10 |  | Merge |  |  | Merge in other css |  |  |  |  | 2019-07-14 | From other themes
C | 11 |  | Merge |  |  | Merge in javascript |  |  |  |  | 2019-07-14
C | 148 |  | Merge |  |  | Merge in other css |  |  |  |  | 2019-07-15 | From other themes, this will have to be done, generally, on a page to page basis, or as-needed
C | 149 |  | Merge |  |  | Merge in javascript |  |  |  |  | 2019-07-15
C |  |  | Merge |  |  | Merge all copies |  |  |  |  | 2017-01-19 | Migrated
C |  |  | Merge |  |  | Merge social media sections |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | Copy updates from Mujin.ai |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | fontawesome-custom.css |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | socialmedia.css |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | tag.php |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | webfonts.js |  |  |  |  | 2020-06-04
C |  |  | Merge |  |  | Removed ionicons.min.css as its not being currently used. |  |  |  |  | 2020-06-04
D | 3 |  | Review |  |  | Update Google web masters |  |  |  |  | 2016-06-14 | Migrated
D | 14 |  | Review | SiteMap |  | Your Sitemap does not contain any URLs. Please validate and resubmit your Sitemap. arne "Google XML Sitemaps" | Empty Sitemap arne "Google XML Sitemaps" |  |  |  | 2015-03-08 | Migrated
D | 15.4 |  | Review | SiteMap |  | add sitemap, xml |  |  |  |  | 2013-08-27 | Migrated
D | 32 |  | Review |  |  | test frontpage | carousel |  |  |  | 2016-09-23 | Migrated
D | 33 |  | Review |  |  | test frontpage | no carousel |  |  |  | 2016-09-23 | Migrated
D | 49 |  | Review |  |  | insure anything custom to this site is in child |  |  |  |  | 2017-01-19 | Migrated
D | 50 |  | Review |  |  | take out any specialized code | functions |  |  |  | 2019-09-04 | Migrated
D |  |  | Review | test |  | Edge |  |  |  |  | 2016-09-23 | Migrated
D |  |  | Review | test |  | IE |  |  |  |  | 2016-09-23 | Migrated
D |  |  | Review | test |  | Safari |  |  |  |  | 2016-09-23 | Migrated
D |  |  | Review | test |  | Chrome |  |  |  |  | 2016-09-23 | Migrated
D |  |  | Review |  |  | move generic non-theme code to utility.php |  |  |  |  | 2017-01-19 | Migrated
D |  |  | Review |  |  | Use get_template_directory() rather than TEMPLATEPATH to return the template path. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | Use get_stylesheet_directory() rather than STYLESHEETPATH to return the stylesheet path. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | Use *_url() template tags, rather than bloginfo() equivalents. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | Avoid hard coding to modify content. Instead, use function parameters, filters and action hooks where appropriate. For example wp_title should be modified using a filter. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | Able to have child themes made from them. (Child theme ready) |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | The theme tags in style.css and description must match the what the theme actually does in respect to functionality and design. (See: Theme Tag List) |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | Use template tags and action/filter hooks properly. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.wp-caption css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.wp-caption-text css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.sticky css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.screen-reader-text css class is needed in your theme css. See See: the Codex for an example implementation. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.gallery-caption css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.bypostauthor css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.alignright css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.alignleft css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED:.aligncenter css class is needed in your theme css. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: This theme doesn't seem to display tags. Modify it to display tags in appropriate locations. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: This theme contains no sidebars/widget areas. See Widgets API |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | WARNING: Your theme appears to be in the wrong directory for the theme name. The directory name must match the slug of the theme. This theme's correct slug and text-domain is digitalzenworks-bootstrap-theme. (If this is a child theme, you can ignore this error.) |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | WARNING: The theme uses the add_shortcode() function. Custom post-content shortcodes are plugin-territory functionality. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | WARNING: Found wrong tag, remove from your style.css header. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | WARNING: Both DOS and UNIX style line endings were found in the file style.css. This causes a problem with SVN repositories and must be corrected before the theme can be accepted. Please change the file to use only one style of line endings. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: The <title> tags can only contain a call to wp_title(). Use the wp_title filter to modify the output |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: No content width has been defined. Example: if ( ! isset( $content_width ) ) $content_width = 900; |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Found a Customizer setting that did not have a sanitization callback function. Every call to the add_setting() method needs to have a sanitization callback function passed. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find the comment-reply script enqueued. See: Migrating Plugins and Themes to 2.7/Enhanced Comment Display <?php if ( is_singular() ) wp_enqueue_script( "comment-reply" ); ?> |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find wp_link_pages. See: wp_link_pages | <?php wp_link_pages( $args ); ?> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find wp_footer. See: wp_footer | <?php wp_footer(); ?> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find post_class. See: post_class | <div id="post-<?php the_ID(); ?>" <?php post_class(); ?>> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find language_attributes. See: language_attributes | <html <?php language_attributes(); ?> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find body_class call in body tag. See: body_class | <?php body_class( $class ); ?> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: Could not find add_theme_support( 'automatic-feed-links' ). See: add_theme_support | <?php add_theme_support( $feature ); ?> |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | REQUIRED: get_current_site_name() found in the file footer.php. Deprecated since version 3.9. Use get_current_site() instead. | Line 2: $site_title = get_current_site_name('name'); |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to post-thumbnails was found in the theme. If the theme has a thumbnail like functionality, it should be implemented with add_theme_support( "post-thumbnails" )in the functions.php file. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to the_post_thumbnail() was found in the theme. It is recommended that the theme implement this functionality instead of using custom fields for thumbnails. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to add_theme_support( "title-tag" ) was found in the theme. It is recommended that the theme implement this functionality for WordPress 4.1 and above. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to add_theme_support( "custom-header", $args ) was found in the theme. It is recommended that the theme implement this functionality if using an image for the header. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to add_theme_support( "custom-background", $args ) was found in the theme. If the theme uses background images or solid colors for the background, then it is recommended that the theme implement this functionality. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: No reference to add_editor_style() was found in the theme. It is recommended that the theme implement editor styling, so as to make the editor content match the resulting post output in the theme, for a better user experience. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: Found the URL of a CDN in the code: maxcdn.bootstrapcdn.com/bootstrap. You should not load CSS or Javascript resources from a CDN, please bundle them with the theme. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | RECOMMENDED: Could not find the file readme.txt in the theme. Please see Theme_Documentation for more information. |  |  |  |  | 2019-09-04 | Migrated
D |  |  | Review |  |  | what is? needed? | sct-color-1 |  |  |  | 2017-01-19 | Migrated
D |  |  | Review |  |  | No exceptions for errors, like include of files |  |  |  |  | 2020-06-04
E | 15.4 |  | Enhancements |  |  | Rich Snippets and data structure | https://support.google.com/webmasters/answer/99170?hl=en |  |  |  | 2013-08-27 | Migrated
E | 20 |  | Enhancements |  |  | Improve dzw SEO header.php |  | 5 |  |  | 2013-06-27 | Migrated
E | 21 |  | Enhancements | SEO |  | Find out about internal 'search' option from google web masters |  |  |  |  | 2016-02-04 | Migrated
E | 30 |  | Enhancements |  |  | carousel vs one picture |  |  |  |  | 2019-09-04 | Migrated
E | 31 |  | Enhancements |  |  | test bootstrap_theme_customizer use_carousel |  |  |  |  | 2019-09-11
E | 150 |  | Enhancements |  |  | The site home page, it should display the blog latest posts. |  |  |  |  | 2019-07-15
E |  |  | Enhancements | Child Theme |  | Test out different naming options |  |  |  |  | 2016-09-23 | Migrated
E |  |  | Enhancements |  |  | No disabling of the admin toolbar. |  |  |  |  | 2019-09-04 | Migrated
E |  |  | Enhancements |  |  | google analytics |  | 30 |  |  | 2013-08-13 | Migrated
E |  |  | Enhancements |  |  | Facebook Pixel |  |  |  |  | 2019-09-11
E |  |  | Enhancements |  |  | add function to enable/disable breadcrumbs |  |  |  |  | 2016-09-23 | Migrated
E |  |  | Enhancements |  |  | add support to include/exclude left site menu |  |  |  |  | 2017-01-19 | Migrated
E |  |  | Enhancements |  |  | sometimes some sites may always want big banner in front |  |  |  |  | 2016-09-23 | Migrated
E |  |  | Enhancements |  |  | reduce banner size |  |  |  |  | 2016-09-23 | Migrated
E |  |  | Enhancements |  |  | add captcha |  |  |  |  | 2017-01-19 | Migrated
E |  |  | Enhancements |  |  | one column page |  |  |  |  | 2019-09-04 | Migrated
E |  |  | Enhancements |  |  | 2 column page, etc |  |  |  |  | 2019-09-04 | Migrated
E |  |  | Enhancements |  |  | Update web font loader |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | Idle Until Urgent |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | Removed media attribute from css link (so then it will use the default 'all' |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | Fix to properly enqueue contact form 7 styles when needed. |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | underlying support for theme custom logo. |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | Moved recaptcha script to after footer. |  |  |  |  | 2020-06-04
E |  |  | Enhancements |  |  | Remove qtransate-xt generator tag. |  |  |  |  | 2020-06-04
F |  |  | Publish |  |  | submit theme |  |  |  |  | 2019-09-04 | Migrated
F |  |  | Publish |  |  | update screenshot |  |  |  |  | 2019-09-04 | Migrated

## Finished
md dir
cd dir
git flow init
npm init
git commit
npm install grunt --save-dev
git commit
gitignore /SourceCode/Web/node_modules
copy style.css
edit style.css comments
git commit
| 1 |  |  | Create WordPress theme
| 4 |  |  | Merge in boilerplate |  |  |  | 2019-07-14
| 5 |  |  | Theme uses the Bootstrap CSS Framework. |  |  |  | 2019-07-14 | Merge in bootstrap
| 2 | Test |  | Define production and development environments |  |  |  | 2019-07-14
| 1 |  |  | Add theme to wps structure |  |  |  | 2019-07-15
| 1 |  |  | npm install grunt-contrib-sass --save-dev |  |  |  | 2019-07-15
| 2 |  |  | npm install grunt-contrib-uglify --save-dev |  |  |  | 2019-07-15
| 3 |  |  | npm install grunt-contrib-watch --save-dev |  |  |  | 2019-07-15
|  |  |  | Create common.scss |  |  |  | 2019-07-19
|  |  |  | Copy normalize.css from boilerplate |  |  |  | 2019-07-19
|  |  |  | Copy and rename boilerplate.css from boilerplate |  |  |  | 2019-07-19
|  |  |  | Copy modernizer.js from boilerplate |  |  |  | 2019-07-19
|  |  |  | Copy plugins.js from bolerpalte |  |  |  | 2019-07-19
Update .gitignore to !js/vendor/
| 4 |  |  | edit Gruntfile.js to include sass |  |  |  | 2019-07-15
| 5 |  |  | edit Gruntfile.js to include uglify |  |  |  | 2019-07-15
| 6 |  |  | edit Gruntfile.js to include watch |  |  |  | 2019-07-15
| 7 |  |  | edit build.cmd to include grunt sass |  |  |  | 2019-07-15
| 8 |  |  | edit build.cmd to include grunt uglify |  |  |  | 2019-07-15
| 9 |  |  | edit build.cmd to include grunt watch |  |  |  | 2019-07-15
| 11 | Test |  | The style.css should used on local development environment for debugging purposes, while the style.min.css should be used on production server for speed optimization purposes. Thus in your code make sure you utilize the appropriate functionality to load each of both CSS files in the right environment. |  |  |  | 2019-07-14 |  | 2019-07-26
| 17 |  |  | The CSS should be generated using SCSS. |  |  |  | 2019-07-19
| 18 |  |  | the SCSS should produce both style.css as well the style.min.css. |  |  |  | 2019-07-14
| 19 |  |  | Minify css and js |  |  |  | 2019-07-14
B | 2 |  |  |  | make dzw child them of bootstrap |  |  |  |  | 2016-06-14 | Migrated
C |  |  | Design |  | responsive |  | 120 |  |  | 2013-08-13 | Migrated
C |  |  |  |  | boilerplate |  | 25 |  |  | 2013-08-13 | Migrated
C |  |  |  |  | minify | http://wordpress.org/plugins/w3-total-cache/installation/ | 35 |  |  | 2013-08-13 | Migrated
A | 26 |  |  |  | Share your code in a Git repository, using the Git Flow workflow, and of course I don't want to see the hole code in a single commit. You should commit as soon as you have a new feature of the theme. |  |  |  |  | 2019-09-04
A | 45 |  |  |  | Share your code in a Git repository, using the Git Flow workflow, and of course I don't want to see the hole code in a single commit. You should commit as soon as you have a new feature of the theme. |  |  |  |  | 2019-09-04
A | 1 |  |  |  | Merge in _s theme | PHP templates |  |  |  | 2019-07-19
A | 3 |  |  |  | make sure all basic files exist |  |  |  |  | 2019-09-04 | Migrated
A | 3 |  |  |  | Merge in _s theme | functions.php |  |  |  | 2019-07-19
A | 4 |  |  |  | Merge in _s theme | inc |  |  |  | 2019-09-11
A | 5 |  |  |  | Merge in _s theme | js |  |  |  | 2019-09-11
A | 6 |  |  |  | Merge in _s theme | sass |  |  |  | 2019-09-11
Move assets to assets directory
C | 17 |  |  |  | fix cache/seo conflict | https://www.doitwithwp.com/speed-up-wordpress-with-w3-total-cache/ |  |  |  | 2015-03-08 | Migrated
A |  |  | Infrastructure |  | Process localhost config files |  |  |  |  | 2017-01-19 | Migrated
A | 1 |  | Infrastructure |  | Incorporate php sniffer checking |  | 60 |  |  | 2019-09-11 | Review inpsyde plugin, gawa composer.json files
A | 12 |  | Infrastructure |  | The theme should be translatable by using the WordPress functions. |  |  |  |  | 2019-07-14
A | 21 |  | Review |  | WARNING: Found a translation function that is missing a text-domain. Function __, with the arguments 'Use just a static image.' |  |  |  |  | 2019-09-04 | Migrated
A | 22 |  | Review |  | WARNING: Found a translation function that is missing a text-domain. Function __, with the arguments 'Static Image' |  |  |  |  | 2019-09-04 | Migrated
A | 20 |  | Infrastructure |  | Strings are not translatable |  |  |  |  | 2020-06-04
A | 10 |  | Infrastructure |  | Integrate wp i18n make-pot into build script | wp i18n make-pot . languages/my-plugin.pot |  |  |  | 2020-06-08
D | 11 |  | Review |  | Create english po file, if needed |  |  |  |  | 2020-06-08
A | 12 |  | Infrastructure |  | I need you, to export the translation records in the po file. |  |  |  |  | 2019-09-04
Convert files to unix EOL
Convert files to spaces
A |  |  | Infrastructure |  | deal with internal git repo |  |  |  |  | 2020-06-04

## Frozen
A | 13 | Infrastructure | Create translated .mo files | msgfmt -o filename.mo filename.po | 2020-06-08 | Add to build script. Only needed if and when translation files (*.po) are developed.

## CheckList
A | 26 |  |  | Share your code in a Git repository, using the Git Flow workflow, and of course I don't want to see the hole code in a single commit. You should commit as soon as you have a new feature of the theme. |  |  | 2019-09-04
| 11 | Test | The style.css should used on local development environment for debugging purposes, while the style.min.css should be used on production server for speed optimization purposes. Thus in your code make sure you utilize the appropriate functionality to load each of both CSS files in the right environment. |  | 2019-07-14 |  | 2019-07-26
| 17 |  | The CSS should be generated using SCSS. |  | 2019-07-19
| 18 |  | the SCSS should produce both style.css as well the style.min.css. |  | 2019-07-14
| 5 |  | Theme uses the Bootstrap CSS Framework. |  | 2019-07-14 | Merge in bootstrap
| 2 | Test | Define production and development environments |  | 2019-07-14